Project Title: Leveraging Artificial Intelligence for the Digital Preservation and Revitalization of Indigenous Languages in Canada

Project Overview:

This document includes the full research methodology, ethical framework, evaluation strategy, and the implementation schedule.

This project does not aim to replace teachers, Elders, or community-led instruction. Instead, it explores how much AI systems can assist in generating beginner-level educational materials using ethically sourced and publicly available linguistic data.

Institution: Thompson Rivers University

Program: Undergraduate Research Experience Award Program (UREAP)

Researcher: Narshini Chuckowry

Primary Scope: Canada-first Indigenous languages

Data approach: Publicly available online datasets; supplemented by community approved materials

Ethical Framework: FPIC, OCAP, Indigenous Data Sovereignty

Research Questions:

- How can AI and large language models be ethically and effectively employed to transform publicly available Indigenous linguistic materials into accessible and engaging education language-learning content?

- What frameworks can ensure the linguistic authenticity, sensitivity and Indigenous community ownership of AI-generated language resources?

- What community-led validation methods can ensure AI-generated Indigenous language content remains accurate, respectful, and linguistically aligned?

- How does fine-tuning large language models on publicly available Indigenous language data impact the quality and educational usefulness of AI-generated outputs compared to baseline models?

Selected Languages

This project prioritizes these Canadian Indigenous languages based on speaker population and dataset availability.

| Language | Region | Approx Speakers | Key Public Data Sources |
| --- | --- | --- | --- |
| Cree | Prairie provinces | 87875 | Plains Cree Corpus, CommonVoice |
| Inuktitut | Nunavut | 41675 | NRC Nunavut Hansard Corpus |
| Ojibwe | Ontario, Manitoba | 26165 | HuggingFace datasets, FirstVoices |

Data sources and licensing

The project will use publicly available or community-authorized Indigenous language materials. No private, restricted or culturally sensitive materials will be used without explicit community permission. All materials will be reviewed to ensure they are licensed for education or research reuse. Proper attribution will be provided where required. The project will be following the Indigenous data sovereignty principles, ensuring respect for community ownership, control, and cultural sensitivity.

AI System Architecture

The project includes fine-tuning two existing open-source models suitable for low-resource settings.

Thie first one includes Speech Recognition (ASR), with base model Whisper-small (244M parameters), fine-tuned on NRC and CommonVoice data. This will convert the Indigenous language audio to text, and the metric evaluated will be the Word Error Rate (WER).

The other model is for text generation, with base model LLaMa 3.2-3B-Instruct, fine-tuned on LoRA (low-rank adaptation). It will also be quantized by 4-bit for Col

ab compatibility. This will generate beginner educational materials with evaluation being human rubrics and baseline comparison.

LoRA is used for fine-tuning since it trains less than 2% of parameters and reduces GPU memory requirements.

Experimental Evaluation Design

This project employs a baseline and fine-tuned comparative experimental design for both Automatic Speech Recognition and Large Language Model (LLM) components.

For both systems, the same procedure will be followed. The baseline model performance will be evaluated on selected Indigenous language data. The model will be fine-tuned using curated and licensed datasets. The performance will be re-evaluated using identical evaluation metrics, and the quantitative and qualitative results will be compared to assess improvement. This comparison enables measurable performance analysis.

The ASR component will be evaluated using Word Error Rate as primary metric which will be calculated on a held-out validation dataset to quantify transcription accuracy before and after finetuning.

The LLM component will be evaluated using a combination of automatic and human-centered metrics. The automatic metrics includes perplexity which will be the sanity check for model learning stability and BLEU score used for translation or reference-aligned generation. The human evaluation metric rubric assesses linguistic correctness, cultural alignment, educational usefulness, and age appropriateness. Each dimension will be scored on a 1-5 scale.

Week implementation Schedule

| Week | Phase | Date | Tasks |
| --- | --- | --- | --- |
| 1-2 | Data Collection | May 11-17 | - Select Indigenous languages - Draft ethics and FPIC statement - Create dataset inventory spreadsheet - Download and verify licenses - Organize datasets |
| 3 | Environment Setup | May 25-31 | - Accept Meta LLaMa license on HuggingFace - Test Whisper baseline - Test LLaMa baseline - Document baseline performance |
| 4 | Audio Processing | June 1-7 | - Clean corrupted/silent audio - Convert all files to 16kHz mono WAV - Create training manifest CSV - Train-validation split - Run small ASR pipeline test |
| 5 | ASR fine tuning | June 8-14 | - Extract Whisper features - Configure training parameters - Fine-tune on one selected language - Evaluate WER - Save checkpoint - Document results |
| 6 | LLM Dataset Preparation | June 15-21 | - Convert text into instruction format - Add language tags - Verify tokenizer compatibility - Balance dataset - Create final JSON training file |
| 7 | LLM Fine tuning | June 22-28 | - Configure LoRA parameters - Load quantized LLaMA - Run supervised finetuning - Save adapter weights - Test multilingual outputs - Document model behaviour |
| 8 | Prompt Engineering | June 29-July 5 | - Design templates for story, vocabulary list, pronunciation guide, quiz, dialogue - Generate test outputs per language - Log all versions in tracking sheet |
| 9 | Pipeline Integration | July 6 -12 | - Build unified Python class - Integrate ASR to LLM flow - Test on sample audio files - Generate outputs for each language - Debug errors |
| 10 | Internal Evaluation | July 13-19 | - Develop evaluation rubric - Score 10 outputs per language - Compare baseline vs finetuned results - Identify error patterns |
| 11 | Community Validation (if available) | July 20-26 | - Prepare clean validation package - Share selected outputs with reviewer - Collect feedback - Document revisions (If no reviewer is confirmed, structured secondary validation using cross source comparison will be conducted) |
| 12 | Finalization and Reporting | July 27- August 8 | - Compile quantitative metrics - Summarize qualitative findings - Document ethical compliance - Prepare final report |

Key Deliverables

Key deliverables include:

- Development Plan - 10 May

- Dataset inventory spreadsheet + license audit - 17 May

- Ethics and FPIC compliance statement - 17 May

- Baseline model performance report - 24 May

- Preprocessed annotated dataset - 31 May

- Fine tuned Whisper ASR checkpoint + WER results - 7 June

- Fine tuned LLaMA model and LoRA weights - 21 June

- Content generation outputs - 5 July

- Error pattern documentation - 12 July

- Community validation package + feedback report - 19 July

- Community feedback integration - 26 July

- Final research report - 8 August

Ethical Framework

All community participation and supplementary data collection requires documented FPIC. For publicly available online datasets, the project complies with each platforms stated terms.